**Name:**

**Directions:**

* The following software may be used:
  + Excel->Data Analysis
  + Excel QM
  + QM for Windows (PC only)
* Please make sure to insert your answers, including any charts, graphs, or output, on this document. You may be required to also upload original files from Excel or QM for Windows.
* **The calculations are not your final answer. A summary/explanation in your own word for each question posed should be included.**
* Question 8, 9 and 10 use the States Data File to run some calculations. Resulting output is already provided for you. You do NOT need to run any calculations on the States Data File.
* Be sure to put your name on this document and save it to your computer. Upload this Word document as your Unit 7 submission in the course Drop Box.

**Submitting Your Project:**

* Save your project in a location that you will remember and with your full name. When you are ready to submit your project, click on the Dropbox and complete the steps below:
* Click the link that says, “Submit an Assignment.”
* In the “Submit to Basket” menu, select Unit 9 Project.
* In the “Comments” field include your name.
* Click the “Add Attachments” button.
* Follow the steps listed to attach your Word Document.
* You should revisit the Dropbox to view any helpful feedback your instructor has and to retrieve your graded project.
* Make sure that you save a copy of your submitted project.

1. Allen Machines specializes in developing weed-harvesting equipment that is used to clear small lakes of weeds. Allen Machines is contemplating the construction of a machine that would harvest weeds on narrow rivers and waterways. The activities and time in weeks necessary to build one of these experimental machines are shown in the table below.

|  |  |  |
| --- | --- | --- |
| **Activity** | **Immediate Predecessors** | **Time in Weeks** |
| **A** | **none** | **6** |
| **B** | **none** | **5** |
| **C** | **A** | **4** |
| **D** | **A** | **3** |
| **E** | **B** | **2** |
| **F** | **B** | **1** |
| **G** | **C,E** | **2** |
| **H** | **D,F** | **3** |

1. **What is the minimum possible time required for completing the project?**
2. **What is the latest possible time that Activity D may be started without delaying the completion of the project?**
3. **What is the latest finish time for Activity F?**
4. **What is/are the critical path(s)?**

**Explanation: (Please include Gantt Chart and/or Network Graph):**

2. The following is the activity and associated costs for the renovation of the local high school football stadium. The times are in weeks.

|  |  |  |  |
| --- | --- | --- | --- |
| **Activity** | **Immediate Predecessor** | **Time** | **Cost ($)** |
| **A** | **-** | **8** | **10,000** |
| **B** | **-** | **4** | **25,000** |
| **C** | **A** | **6** | **15,000** |
| **D** | **B** | **2** | **30,000** |
| **E** | **B** | **3** | **20,000** |
| **F** | **C, D** | **7** | **12,000** |
| **G** | **C, D** | **5** | **56,000** |
| **H** | **E, F** | **1** | **20,000** |

1. **What is the critical path and total time required for this project?**

**Answer:**

**Explanation: (include Gantt Chart and/or Network Graph):**

1. **How much of the total (cumulative) budget would be spent in Week 8 (Period 8) with the earliest start budget?**

**Answer:**

**Explanation (include cost budgeting table):**

3. Precision Manufacturing has a government contract to produce stainless steel rods for use in military aircrafts. Each rod is required to be 25 millimeters in diameter. Each hour, random samples of size n = 5 rods are measured to check process control. Four hours of observations yielded the following:

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Diameter** | | | | |
| **Time** | **Rod 1** | **Rod 2** | **Rod 3** | **Rod 4** | **Rod 5** |
| **9 A.M.** | **24.5** | **24.9** | **27.9** | **26** | **25.9** |
| **10 A.M.** | **25.1** | **24.7** | **23** | **25.4** | **24.9** |
| **11 A.M.** | **28.9** | **25** | **27.9** | **28.3** | **26.5** |
| **Noon** | **45** | **25.2** | **22.1** | **28.1** | **25** |

1. **Construct the xbar-chart and the R-chart.**

**Please include charts below:**

1. **Is the process in control?**

**xbar chart UCL = R-chart UCL =**

**xbar chart LCL = R-chart LCL =**

**Explanation:**

4. Modern Electronics specializes in manufacturing modern electronic components. It also builds the equipment that produces the components. Modern Electronics is considering building a new facility but the estimated profits would be impacted by the type of market that develops. The probability for a strong market is 0.4; for a fair market is 0.4; and for a poor market is 0.2. You are responsible for advising the president of Modern Electronics on the type facility that should be built or to not build a facility at all. The table shows the estimated profits under each market and for each size facility.

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Estimated Profits** | | |
|  | **Strong Market** | **Fair Market** | **Poor Market** |
| **Build a large facility** | **550,000** | **150,000** | **-500,000** |
| **Build a medium-size facility** | **500,000** | **125,000** | **-150,000** |
| **Build a small facility** | **250,000** | **75,000** | **-25,000** |
| **Do not build a facility** | **0** | **0** | **0** |

1. **What is your recommendation to the president based on expected value that maximizes profits (EMV).**

**Answer:**

**Explanation (include expected monetary value):**

**Software Output:**

1. **Provide a second recommendation to the president that minimizes regret.**

**Answer:**

**Explanation (include expected monetary value):**

**Software Output:**

5. Consulting income at Kaplan Associates for the period February – July is shown in the table below. **Assume that the initial forecast for February is $90,000**. Use Exponential smoothing to forecast August’s income.

|  |  |
| --- | --- |
| **Month** | **Income ($1,000)** |
| **February** | **90.0** |
| **March** | **88.5** |
| **April** | **74.8** |
| **May** | **91.7** |
| **June** | **91.3** |
| **July** | **92.8** |

1. **Use a smoothing constant of α = 0.2.**

**Answer:**

**Explanation (include software output):**

1. **Use a smoothing constant of α = 0.4.**

**Answer:**


**Explanation (include software output):**

1. **Analysis of the forecasting errors indicates which forecasting constant is best in this situation?**

**Answer:**

**Explanation (include software output):**

6. Johnson Construction Company is in the process of installing power lines to a large housing development. The company wants to minimize the total length of wire used, which would minimize the company’s cost. The housing development is shown below. Each house has been numbered, and the distances between houses are given in hundreds of feet.



1. **What do you recommend to Johnson Construction Company?**

**Answer:**

**Explanation (including software output):**

7. The storm drains in the Cedar Rapids, Iowa, have been upgraded following the devastating floods of 2008. The network of storm drains and the capacities are shown below. **Determine the maximum flow (in hundreds of gallons of water per minute) from node 1 to node 5.** Remember that the arc has both capacity and reverse capacity.

|  |  |  |
| --- | --- | --- |
| From Node | To Node | Fluid Flow |
| 1 | 2 | 350 |
| 2 | 1 | 150 |
| 1 | 3 | 75 |
| 3 | 1 | 100 |
| 1 | 4 | 200 |
| 4 | 1 | 500 |
| 1 | 5 | 250 |
| 5 | 1 | 300 |
| 2 | 4 | 100 |
| 4 | 2 | 400 |
| 3 | 4 | 200 |
| 4 | 3 | 250 |
| 3 | 5 | 150 |
| 5 | 3 | 550 |
| 4 | 5 | 250 |
| 5 | 4 | 100 |

**Answer:**

.

**Explanation (include software output):**

8. From the States Data Set the following output for **Poverty** and for the **Population** was created.



1. **Which variable has the greatest relative variation?**

**Answer:**

.

**Explanation (include any calculations):**

9. You are a consultant working for Kaplan Consulting. The U.S. Department of Labor has requested assistance in evaluating the impact of economic stimulus on the unemployment rate. From the States Data Set the following t-test was conducted to answer the question:   
**“Has there been a significant reduction in the national unemployment rate between January and February?”**

**Output from PhStat2 : Output from Excel-DataAnalysis:**



1. **What is the Null and the Alternative Hypotheses?**

**Ho:**

**Ha:**

1. **What is your level of alpha (α)?**
2. **What is your decision about the hypothesis based on the software output?**
3. **Has there been a significant reduction in the national unemployment rate between January and February?**

10. The Governor of a southern state has asked Kaplan Consulting to determine if the state were able to increase the percentage of its population with a Bachelor’s Degree to 50%, what might be the expected median household income based on 2000 data? Here is the output from the Regression procedure from Excel.



1. **What would be the predicted median household income if the percentage of the population in the state were 50% or 50?**

**Answer:**

.

**Explanation (include any calculations):**