Work Breakdown Structure

- Virtual Private Cloud Implementation (VPCI)

  - Initiation

    - Evaluation and Recommendations

    - Develop Project Charter

    - Submit Project Charter

    - Project Sponsor Reviews Project Charter

    - Project Charter Signed/Approved

  - Planning

    - Create Preliminary Scope Statement

    - Determine Project Team

    - Project Team Kickoff Meeting

    - Develop Project Plan

    - Submit Project Plan

    - Project Plan Approved (Milestone)

  - Execution

    - Project Kickoff Meeting

    - Verify and Validate User/Sponsor Requirements

    - Design Cloud Server Environment

    - Provide Recommendations for SANs

    - Purchase Cloud servers and SANs workstations

    - Set-up Cloud Environment & SAN

    - Test connectivity & Accessibility

    - Transfer Data from existing servers

    - Confirm Accessibility of data

    - Create Backup using Microsoft Azure

    - User Training

    - Go Live with Cloud for new data

  - Control

    - Project Management

    - Project Status Meetings

    - Risk Management

    - Update Project Management Plan

  - Close-out

    - Audit Procurement

    - Document Lessons Learned

    - Update Files & Records

    - Gain Formal Acceptance

    - Archive Files & Document

Scope Statement

Project Purpose and Justification	2

Scope Description	2

High Level Requirements	2

Boundaries	3

Risk		3

Strategy	4

Deliverables	4

Acceptance Criteria	5

Constraints	5

Assumptions	6

Cost Estimate	7

Cost Benefit Analysis	9

Cost References	10

# Project Purpose and Justification

This project has been approved to provide professional services for a Virtual Private Cloud Implementation (VPCI) for the City of Palo Alto. The scope is to include the planning, purchase, installation, and testing of a virtual private cloud with backups in Microsoft Azure.

# Scope Description

The scope of the project is to provide the planning, purchase, installation, and testing of

a virtual private cloud with backups in Microsoft Azure. This will include providing recommendations for a Storage Area Network (SAN) for the virtualization to include all required specifications to ensure a successful data transfer and continuing storage.

# High-Level Requirements

The Virtual Private Cloud Implementation (VPCI) project has been approved to meet the City of Palo Alto’s need for replacement of physical computer servers providing space and flexibility for the City’s data management and storage needs. To address these requirements, there are several requirements which must be fulfilled as part of the successful execution of this project. The following high-level requirements have been identified for the VPCI Project:

- Planning for a virtual private cloud with backups in Microsoft Azure

- Purchase of required material, services, labor and maintenance for a virtual private cloud with backups in Microsoft Azure

- Installation of a virtual private cloud with backups in Microsoft Azure

- Test of a virtual private cloud with backups in Microsoft Azure

- Recommendations for a Storage Area Network (SAN) for virtualization to include all required  specifics

- Optional On-Call Provision for maintenance and technical support

# Boundaries

The VPCI Project includes all work associated with planning, purchase, installation, and testing of a virtual cloud server for the City of Palo Alto. The boundaries are further defined in the following sections.

Risk

The migration of data for the City of Palo Alto from the currently housed server to a cloud management system will house some inherent risks.  Those that pose a potential detriment to this project are identified and may be avoidable.

- Malware

- Hackers

- Lack of Specifics for SAN’s

- System Misconfigurations

- Data leakage

- Human Resource Demands

- Regulatory Compliance

- Business Continuity

- Service and Data Integration

- Insecure API’s

- Data Ownership and Accountability

# Strategy

For the VPCI Project strategy, the project team will leverage the expertise of its diversified project team members from the Group 4 Project Management Team. They will aid the project manager and other team members in conceptual and technical design, coding, server configuration, testing and troubleshooting, and deployment. The project manager will ensure that IT experts are utilized to incorporate all input from stakeholders and gathered requirements.

# Deliverables

There are several deliverables which will be produced as a result of the successful completion of the VPCI Project. If all of the following deliverables are not met, then the project will not be considered successful. The Project Manager is responsible for ensuring the completion of these deliverables.The deliverables are listed below:

- Virtual private cloud solution (Architecture and hardware recommendation)

- Virtual private cloud implementation plan (Including procurement of the recommended hardware)

- Redundancy strategy recommendation (Utilizing Microsoft Azure)

- SAN installed and available on the City Network

- Working HyperV cluster connected to SAN storage environment

- Backup to Azure established and tested

- Training of staff in use of implemented solution

- Operational documentation for storage solution and redundancy in Azure

# Acceptance Criteria

Acceptance criteria have been established for the VPCI Project to ensure thorough vetting and successful completion of the project. The acceptance criteria are both qualitative and quantitative in nature. All acceptance criteria must be met to achieve success for this project:

- Meet all deliverables within schedule and budget tolerances

- Backup system installed and tested successfully under all predictable scenarios

- 25% increase in technical productivity for data center

- 90% virtualization of all servers

- Cloud install complete and 98% error free

- Training of all users completed successfully

- Previous data transferred, tested, and confirmed accessible

# Constraints

Several constraints have been identified for the VPCI Project. It is imperative that considerations be made for these constraints throughout the project lifecycle. All stakeholders must remain mindful of these constraints as they must be carefully planned for to prevent any adverse impacts to the project’s schedule, cost, or scope. The following constraints have been identified for the VPCI Project:

- Project must be completed by the end of August 2014

- Project must be completed within not-to-exceed budget

- Project must utilize Microsoft Azure as backup

- Security and data protection are needed but not specified

- Efficient energy use (Green)

- Eliminate risk of sustained outage (disaster recovery)

- Lower recovery time from an outage (disaster recovery)

# Assumptions

Several assumptions have been identified for the VPCI Project. All stakeholders must be mindful of these assumptions as they introduce some level of risk to the project until they are confirmed to be true. During the project planning cycle every effort must be made to identify and mitigate any risk associated with the following assumptions:

- Stakeholder and user testing will provide additional data and feedback midway through the project.

- Data center requires 90% of servers virtualized but will maintain 10% physical

- The city expects user manuals to assist data center staff in using cloud servers, but not a required deliverable. Team assumes a soft copy manual will be provided at completion of project and updated upon execution of any option

- Work will be done onsite at City of Palo Alto data center and off-site at cloud facility

- City of Palo Alto data center will be capable of providing required temperature controlled environment for installation of new servers and access for maintenance purposes

- The project team will be provided any required badging and access necessary to complete the project. This is to include on-site workstations at the City of Palo Alto data center provided by the City

- Approval of the SAN recommendations within ten (10) days of project start to ensure no impact to schedule

# Cost Estimate

The cost estimates for this project are included in the table below. As the project proceeds and any additional costs become known, this cost estimate will be refined and communicated to all project stakeholders.

| Line Item | Labor | Material | Other | Total |
| --- | --- | --- | --- | --- |
| 1. Project Initiation |  |  |  |  |
| 1.1 Develop Project Charter/Plan | $3,000.00 | $500.00 |  | $3,500.00 |
| 2. Project Planning |  |  |  |  |
| 2.1 Research and Project Development | $12,000.00 | $500.00 |  | $12,500.00 |
| 2.2 Layout Cloud | $6,000.00 | $500.00 |  | $6,500.00 |
| 3. Project Execution |  |  |  |  |
| 3.1 Redesign Data Center | $12,000.00 | $500.00 | $2,000.00 – Travel | $14,500.00 |
| 3.2 Install and Test | $48,000.00 | $4,700.00 | $2,000.00 – Travel | $54,700.00 |
| 3.3 Initiate Azure Service | $12,000.00 | $500.00 | $400,000.00 – est. service $2,000.00 – Travel | $414,500.00 |
| 3.4 Create User Manual | $6,000.00 | $500.00 |  | $6,500.00 |
| 3.5 Complete Implementation | $72,000.00 |  | $2,000.00 – Travel | $74,000.00 |
| 4. Close Project |  |  |  |  |
| 4.1 Review Meetings and Feedback, Correction of any errors | $12,000.00 | $500.00 |  | $12,500.00 |
| Project Total | $183,000.00 | $8,200.00 | $408,000.00 | $599,200.00 |

# Cost Benefit Analysis

A cost-benefit analysis has been provided for the VPCI Project. The successful completion of this project will provide significant benefits to the City of Palo Alto. It is imperative that all stakeholders understand these benefits, as well as, the importance of the successful completion of this project. The table below shows a net benefit of $750,800.00 over one year after successful completion of the Project. This benefit is based on the City’s current data management infrastructure and operations and assumes no schedule delays, cost overruns, or lack of resource allocation for the benefit to occur.

| Costs |  | Benefits |  |
| --- | --- | --- | --- |
| Implementation, one-time | $599,200.00 | Labor Reduction, annual | $100,000.00 |
| Maintenance, annual | $4,800,000.00 | Server Maintenance Reduction, annual | $50,000.00 |
|  |  | Risk Reduction, one-time | $5,900,000.00 |
|  |  | Quality Improvement, annual | $100,000.00 |
| Total, 1 year | $5,399,200.00 |  | $6,150,000.00 |
| Benefit |  |  | $750,800.00 |

# Cost References

Azure Microsoft (n.d.). Backup Pricing. Retrieved from: https://azure.microsoft.com/en-us/pricing/details/backup/ (2017, Jun 25).

Expedient.com (n.d.) The Complete Cloud Build vs. Buy Calculator. Retrieved from: https://www.expedient.com/cloud-build-vs-buy-calculator/ (2017, Jun 25)

Google.com (n.d.). Google SQL Cloud Pricing. Retrieved from: https://cloud.google.com/sql/ (2017, Jun 25).

Marks, G. (2013, Apr 9). Do You Replace Your Server Or Go To The Cloud?
The Answer May Surprise You.
Retrieved from: https://www.forbes.com/sites/quickerbettertech/2013/04/29/do-you-replace-your-server-or-go-to-the-cloud-the-answer-may-surprise-you/#5ec709485869 (2017, Jun 25).

Payscale.com (n.d.) Salary estimates
retrieved from: http://www.payscale.com/ (2017, Jun 25).

Rackspace.com (n.d.). High-Performance Virtual Cloud Servers Help You
Grow and Maximize Your Business.
Retrieved from: https://www.rackspace.com/cloud/servers (2017, Jun 25).

Singh, S. and Jangwal, T. (April 2012) Cost breakdown of Public Cloud Computing and
Private Cloud Computing.
International Journal of Computer Science & Information Technology (IJCSIT)
Vol 4, No 2. Retrieved from: http://airccse.org/journal/jcsit/0412csit02.pdf (2017, Jun 25).

Smartfile.com
(n.d.) How Much Does It Really
Cost To Setup And Maintain Your Own FTP Server? Retrieved from: https://www.smartfile.com/blog/cost-setup-maintain-ftp-server/ (2017, Jun 25).

Smith, D. (2003). The Cost of Lost Data. Retrieved from: https://gbr.pepperdine.edu/2010/08/the-cost-of-lost-data/ (2017, Jul 8).